## Worksheet
Ser | Letter No | Date | From | To | Subject: | Department | Assigned To | Status | Due Date | Letter Type | Reference Letter No | Remarks
1 | DD-OD-11190-91-02-623 | 2023-05-02 | HSL | NHQ | Anchor capstan GRAQ - DSV | OD | Avinash | Completed | 2023-05-10 | Outward | SP/10000/GRAQ
2 | DD-OD-11190-91-02-626 | 2023-05-08 | HSL | NHQ | DIVING SYSTEM STORES - DSV | OD | Sravya | Completed | 2023-05-18 | Outward | WOT/DSV/Diving
3 | DD/OD/11190-91/02/628 | 2023-05-10 | HSL | NHQ | Diving system - SPHL Fats report in comments - UH response VC11190-91 - 02xDSVs | OD | Sravya | Pending | 2023-05-20 | Outward
4 | DD/OD/11190-91/02/627 | 2023-05-10 | HSL | NHQ | Diving System - Booster Model - 02xDSVs | OD | Sravya | Pending | 2023-05-20 | Outward
5 | DD/OD/11190-91/02/629 | 2023-05-10 | HSL | NHQ | Diving system - FMECA & ship system IRS approval | OD | Sravya | Pending | 2023-05-15 | Outward
6 | DD/OD/11190-91/02/630 | 2023-05-10 | HSL | NHQ | Main Signal Office - CAT A compartment | MD | Srikanth | Pending | 2023-05-20 | Outward
7 | DD/MD/11190-91/GRAQ-203/2023 | 2023-05-11 | HSL | NHQ | Approval of 2MW & 3MW DG set GRAQs - 02xDSVs | MD | Srikanth | Pending | 2023-05-18 | Outward
8 | PP-PL-DSVs-MODs-420-2023 | 2023-05-12 | HSL | NHQ | UIG MOD | PP | Rajendra | Pending | 2023-05-20 | Outward
9 | DDMD1190-91GRAQ-2032023-APPROVAL OF 2 MW & 3MW DG SET GRAQs - 02XDSV | 2023-05-19 | HSL | NHQ | DDMD1190-91GRAQ-2032023-APPROVAL OF 2 MW & 3MW DG SET GRAQs - 02XDSV | MD | Srikanth | Pending | 2023-05-30 | Outward
10 | PP-PL-DSVs-CPRM-423-2023 Dt.20-05-23 - On site review of Diving Eqpt. - 02xDSVs | 2023-05-20 | HSL | NHQ | PP-PL-DSVs-CPRM-423-2023 Dt.20-05-23 - On site review of Diving Eqpt. - 02xDSVs | PP | Rajendra | Completed | 2023-05-28 | Outward | SP/10000/CPRM
11 | DD-ED-DSV-COSGRAQ-317-23-Approval of ACOS-HCOS GRAQs | 2023-05-22 | HSL | NHQ | DD-ED-DSV-COSGRAQ-317-23-Re Letter from WOT COMMENTS ADDITIONAL INPUTS FOR ACOS & HCOS GRAQS - 02 x DSVs | ED | Phaneendra reddy | Completed | 2023-05-29 | Outward | WOT/DSV/GRAQ
12 | DD/OD/11190-91/02/644 | 2023-05-31 | HSL | NHQ | Vc11190-91 RIGGING WARRANT_02xDSV | OD | Avinash | Completed | 31-06-2023 | Outward | SP/10000/Hull Dwg (ii)
13 | DD-ED-DSV-IPMS-395-23 | 2023-05-31 | HSL | NHQ | 30 May 23_Letter to WOT_IPMS Dynamic Analysis | ED | Rajanikanth | Completed | 31-06-2023 | Outward | WOT/DSV/Engg(i)
14 | DD-OD-11190-91-02-643 | 2023-05-31 | HSL | NHQ | Compartment Numbering-DSV | OD | Avinash | Completed | 31-06-2023 | Outward | WOT/DSV/GC
15 | PP-PL-DSVs-MODs-428-2023 | 2023-05-31 | HSL | NHQ | Letter to WOT_MODs FOR ADDITIONAL MEDICAL EQUIPMENT - 02 X DSVs | PP | Rajendra | Completed | 2023-05-31 | Outward | SP/10000/MOD
16 | DD-ED-DSV-MSB GRAQ-396-23 | 2023-06-01 | HSL | NHQ | approval of MSB and ESB GRAQS-VC11190-91 | ED | Phaneendra reddy | Completed | 2023-06-10 | Outward | WOT/DSV/GRAQs
17 | DD-ED-DSV-VSE GRAQ-397-23 | 2023-06-01 | HSL | NHQ | Letter to WOT (V) for Approval of Visual Signalling equipment GRAQs VC 11190-91 | ED | Phaneendra reddy | Completed | 2023-06-15 | Outward | WOT/DSV/GRAQs
18 | DD-ED-DSC-GRAQ-398-23 | 2023-06-02 | HSL | NHQ | Re Letter to WOT Documents Required for Approval of GRAQs - 02 x DSVs | ED | Phaneendra reddy | Pending | 2023-06-12 | Outward
19 | PP-PL-DSVs-PMF-431-2023 | 2023-06-02 | HSL | NHQ | Letter to WOT - Project Monitoring Staff - 02xDSVs | PP | Rajendra | Pending | 2023-06-12 | Outward
20 | DD-ED-DSV-ESS-GRAQ-399-23 | 2023-06-03 | HSL | NHQ | Re Letter to WOT Documents Required for Approval of GRAQs - 02 x DSVs | ED | Rajendra | Pending | 2023-06-13 | Outward
21 | DD/MD/11190-91/ME - 215/2023 | 2023-06-05 | HSL | NHQ | Onboard Observations- WOT(V) | MD | Srikanth | Completed | 2023-06-15 | Outward | WOT/DSV/GC dated 18 May 23
22 | PP-PL-DSVs-MODs-434-2023 | 2023-06-05 | HSL | NHQ | UID MOD | PP | Rajendra | Completed | 2023-06-15 | Outward | PP/PL/DSVs/MODs/420/2023 dated 12 May 23
23 | PP-PLlDSVs- PMF- 433-2023 | 2023-06-05 | HSL | NHQ | LETTER TO WOT - PROJECT MONITORING STAFF - 02 X DSVs | PP | Rajendra | Completed | 2023-06-15 | Outward | PP-PL-DSVs-PMF-431-2023
24 | DD/MD/11190-91/GRAQ - 216/2023 | 2023-06-05 | HSL | NHQ | Letter_to_WOT_V_GRAQs_LO_FO_BALLAST_SYSTEM | MD | Srikanth | Completed | 2023-06-05 | Outward | WOT/DSV/GRAQs(i) dated 25 May 23.
25 | DD-MD-11190-91-GRAQ-218-2023 | 2023-06-06 | HSL | NHQ | HSL-DSV-GRAQs-2MW and 3MW DA GRAQs for approval | MD | Srikanth | Completed | 2023-06-06 | Outward | WOT/DSV/ENGG dated 05 Jun 23
26 | DD/OD/11190-91/02/641 | 2023-06-06 | HSL | NHQ | Vc11190-91 Heat Input Test GRAQS-02xDSV | OD | Srikanth | Completed | 2023-06-06 | Outward | SP/10000/GRAQ dated 23 Jun 23
27 | DD/ ED/ DSV/ ICD/ 405 / 23 | 2023-06-08 | HSL | NHQ | 11190-91 Letter to IHQ and WOT for ICD status of DSVs | ED | Sarojini | Completed | 2023-06-08 | Outward | SP/10000/PLIT & ICM dated 06 Jun 23
28 | DD-ED-DSV-MODCMS-408-23 | 2023-06-13 | HSL | NHQ | 11190-91 Letter to IHQ and WOT for amended date of FATs for CMS | ED | Sarojini | Completed | 2023-06-13 | Outward | DD - ED - DSV-MODCMS-403-23
29 | DD-ED-DSV-APMS GRAQ-407-23 | 2023-06-13 | HSL | NHQ | APMS GRAQs & Annexures | ED | Phaneendra reddy | Completed | 2023-06-13 | Outward | WOT/DSV/GRAQ dated 08 Jun 23
30 | PP-PL-DSVs-MODs-441-2023 | 2023-06-13 | HSL | NHQ | Documents of HPWMFFS & 15T Crane | PP | Rajendra | Completed | 2023-06-13 | Outward | SP/10000/MOD dated 06 Jun 23
31 | DD-ED-DSV-TRU GRAQ-409-23 | 2023-06-14 | HSL | NHQ | Approval of GRAQ for TRU cum battery charger_VC 11190-91 | ED | Phaneendra reddy | Completed | 2023-06-14 | Outward | WOT-DSV-GRAQs(i) Dt, 02 May 23
32 | DD-MD-11190-91-015-2023 | 2023-06-15 | HSL | NHQ | Withdrawal Arrangements Drawings of DSVs | MD | Srikanth | Completed | 2023-06-15 | Outward | SP/10000/Engg Dwg dated 05 Apr 23
33 | DD-OD-11190-91-02-648 | 2023-06-15 | HSL | NHQ | Letter to WOT_ UMBILICAL WINCHES-DSV | OD | Sravya | Completed | 2023-06-15 | Inward | DD/OD/11190-91/02/647 dated 13 Jun 23
34 | DD/OD/11190-91/02/652 | 2023-06-21 | HSL | NHQ | RAS arrangement - DSV | OD | Avinash | Completed | 2023-06-21 | Inward | SP/1000/Hull Dt.15-06-23
35 | PP/PL/DSVs/B&D/MOD/450/2023 | 2023-06-22 | HSL | NHQ | B&D spares for DG sets (02 MW & 03 MW) - 02xDSVs | PP | Rajendra | Completed | 2023-06-22 | Inward | SP/10000/B&D Dt.12-06-23
36 | DD/MD/11190-91/GRAQs/224/2023 | 2023-06-23 | HSL | NHQ | Approval of GRAQ for Fresh Water Filling and Transfer System including Fresh Water pumps for 02xDSVs | MD | Srikanth | Completed | 2023-06-23 | Inward | WOT/DSV/GRAQ Dt.16-06-23
37 | DD/ED/DSV/DG_LCP/41/23 | 2023-06-23 | HSL | NHQ | Accessibilty of Port DG LCP - VC11190-91 | ED | Phaneendra reddy | Completed | 2023-06-23 | Inward | WOT/DSV/GC Dt.02-03-23
38 | DD/ED/DSV/FDR/415/23 | 2023-06-23 | HSL | NHQ | Flight deck recorder interface with ACCS Radios - VC11190 & 91 | ED | Phaneendra reddy | Pending | 2023-06-23 | Inward | WOT/DSV/ELE Dt.28-03-23
39 | DD/ED/DSV/LED LTG/416/23 | 2023-06-23 | HSL | NHQ | LED based AELs & 24V DC Light fittings for VC11190-91 | ED | Phaneendra reddy | Pending | 2023-06-23 | Inward | SP/10000 Dt.29-05-23
40 | DD/MD/11190-91/DOCS-167/2023 | 2023-06-27 | HSL | NHQ | Forwarding of system documentation - 02xDSVs | MD | Srikanth | Pending | 2023-06-27 | Inward | WOT/DSV/ENGG dated 05 Jun 23
41 | DD/ED/DSV-FMEA/419/23 | 2023-06-26 | HSL | NHQ | FMEA of DP system - 02xDSVs (VC11190-91) | ED | Rajanikanth | Pending | 2023-06-26 | Inward | WOT/DSV/DP Dt.18-05-23
42 | DD/MD/11190-91/PS-01/2023 | 2023-06-28 | HSL | NHQ | FATs of HPWMFFS - 02xDSVs | MD | Srikanth | Pending | 2023-06-28 | Inward | SP/10000/FAT Dt.26-06-23
43 | SP/10000/GRAQ | 2023-06-10 | NHQ | HSL | Vc11190-91 RIGGING WARRANT_02xDSV | OD | Avinash | Pending | 2023-06-10 | Inward
44 | WOT/DSV/Diving | 2023-07-15 | WOT | HSL | 30 May 23_Letter to WOT_IPMS Dynamic Analysis | OD | Sravya | Pending | 2023-07-15 | Inward
45 | SP/10000/FATs | 2023-07-16 | NHQ | HSL | Compartment Numbering-DSV | OD | Sravya | Pending | 2023-07-16 | Inward
46 | WOT/DSV/Diving | 2023-07-17 | WOT | HSL | Letter to WOT_MODs FOR ADDITIONAL MEDICAL EQUIPMENT - 02 X DSVs | OD | Sravya | Pending | 2023-07-17 | Inward
47 | SP/10000/Diving | 2023-07-18 | NHQ | HSL | approval of MSB and ESB GRAQS-VC11190-91 | OD | Sravya | Pending | 2023-07-18 | Inward
48 | SP/10000 | 2023-07-19 | NHQ | HSL | Letter to WOT (V) for Approval of Visual Signalling equipment GRAQs VC 11190-91 | MD | Srikanth | Pending | 2023-07-19 | Inward
49 | SP/10000/GRAQ | 2023-07-20 | NHQ | HSL | Re Letter to WOT Documents Required for Approval of GRAQs - 02 x DSVs | MD | Srikanth | Pending | 2023-07-20 | Inward
50 | WOT/DSV/MOD | 2023-07-21 | WOT | HSL | Letter to WOT - Project Monitoring Staff - 02xDSVs | PP | Rajendra | Pending | 2023-07-20 | Inward
51 | SP/10000/GRAQ | 2023-07-22 | NHQ | HSL | Re Letter to WOT Documents Required for Approval of GRAQs - 02 x DSVs | MD | Srikanth | Pending | 2023-07-20 | Inward
52 | SP/10000/CPRM | 2023-05-19 | NHQ | HSL | Onboard Observations- WOT(V) | PP | Rajendra | Pending | 2023-07-20 | Inward
53 | WOT/DSV/GRAQ | 2023-05-20 | WOT | HSL | UID MOD | ED | Phaneendra reddy | Pending | 2023-07-20 | Inward
54 | SP/10000/Hull Dwg (ii) | 2023-05-22 | NHQ | HSL | LETTER TO WOT - PROJECT MONITORING STAFF - 02 X DSVs | OD | Avinash | Pending | 2023-07-20 | Inward
55 | WOT/DSV/Engg(i) | 2023-05-31 | WOT | HSL | Letter_to_WOT_V_GRAQs_LO_FO_BALLAST_SYSTEM | ED | Rajanikanth | Pending | 2023-07-20 | Inward
56 | WOT/DSV/GC | 2023-05-31 | WOT | HSL | HSL-DSV-GRAQs-2MW and 3MW DA GRAQs for approval | OD | Avinash | Pending | 2023-07-20 | Inward
57 | SP/10000/MOD | 2023-07-19 | WOT | HSL | Vc11190-91 Heat Input Test GRAQS-02xDSV | PP | Rajendra | Pending | 2023-07-20 | Inward
58 | WOT/DSV/GRAQs | 2023-07-20 | WOT | HSL | 11190-91 Letter to IHQ and WOT for ICD status of DSVs | ED | Phaneendra reddy | Pending | 2023-07-20 | Inward
59 | WOT/DSV/GRAQs | 2023-07-21 | WOT | HSL | 11190-91 Letter to IHQ and WOT for amended date of FATs for CMS | ED | Phaneendra reddy | Pending | 2023-07-20 | Inward
60 | WOT/DSV/GRAQs | 2023-05-20 | WOT | HSL | APMS GRAQs & Annexures | ED | Phaneendra reddy | Pending | 2023-07-20 | Inward
61 | WOT/DSV/PMF | 2023-05-22 | WOT | HSL | Documents of HPWMFFS & 15T Crane | PP | Rajendra | Pending | 2023-07-20 | Inward
62 | WOT/DSV/GRAQs DATED 25 May 23 | 2023-05-31 | WOT | HSL | Approval of GRAQ for TRU cum battery charger_VC 11190-91 | ED | Rajendra | Pending | 2023-07-20 | Inward
63 | WOT/DSV/GC dated 18 May 23 | 2023-05-31 | WOT | HSL | Withdrawal Arrangements Drawings of DSVs | MD | Srikanth | Pending | 2023-07-20 | Inward
64 | PP/PL/DSVs/MODs/420/2023 dated 12 May 23 | 2023-05-31 | HSL | NHQ | Letter to WOT_ UMBILICAL WINCHES-DSV | OD | Sravya | Pending |  | Outward
65 | PP-PL-DSVs-PMF-431-2023 | 2023-05-31 | HSL | NHQ | RAS arrangement - DSV | MD | Srikanth | Pending |  | Outward
66 | WOT/DSV/GRAQs(i) dated 25 May 23. | 2023-06-01 | WOT | HSL | B&D spares for DG sets (02 MW & 03 MW) - 02xDSVs | MD | Srikanth | Pending | 2023-07-20 | Inward
67 | WOT/DSV/ENGG dated 05 Jun 23 | 2023-06-01 | WOT | HSL | Approval of GRAQ for Fresh Water Filling and Transfer System including Fresh Water pumps for 02xDSVs | PP | Rajendra | Pending | 2023-07-20 | Inward
68 | SP/10000/GRAQ dated 23 Jun 23 | 2023-06-02 | NHQ | HSL | Accessibilty of Port DG LCP - VC11190-91 | MD | Srikanth | Pending | 2023-07-20 | Inward
69 | SP/10000/PLIT & ICM dated 06 Jun 23 | 2023-06-03 | NHQ | HSL | Flight deck recorder interface with ACCS Radios - VC11190 & 91 | PP | Rajendra | Pending | 2023-07-20 | Inward
70 | DD - ED - DSV-MODCMS-403-23 | 2023-06-04 | HSL | NHQ | LED based AELs & 24V DC Light fittings for VC11190-91 | ED | Phaneendra reddy | Pending |  | Outward
71 | WOT/DSV/GRAQ dated 08 Jun 23 | 2023-06-05 | WOT | HSL | Forwarding of system documentation - 02xDSVs | ED | Phaneendra reddy | Pending | 2023-07-20 | Inward